## Sheet1
12 Car Organiser Checklist
Guidance sheet ref | Activity | Responsibility | Target date | Complete | Comments
8 weeks before the event
1 | Identify start/finish venue, contact and book
Arrange food scope and cost
Create an event budget and adjust entry fee or food costs to ensure event is within budget
Decide entry fee
2 | Draw out route on landranger map
3 | Drive route to check mileage
Decide on time control positions
4 | Make tracing of route and send to RLO
5 | Apply for permit via Motorsport UK website or Club Committee member
6 | Produce event regulations
Produce advert for event
6 weeks before event
7 | Notify police of event
8 | Arrange insurance with provider
Send out insurance documentation to entrants
4 weeks before event
9 | Confirm control positions and number of marshals required
10 | Design navigational instructions for Experts
Design navigational instructions for Semi-Experts
Design navigational instructions for Novices
Have navigational instructions checked
11 | Send out event reminder
12 | Collect clocks and code boards
Final week before event
13 | Print navigational instructions for Experts
Print navigational instructions for Semi-Experts
Print navigational instructions for Novices
Print maps for Beginners
14 | Print Marshal instructions
15 | Print final instructions for competitors
16 | Print letter To Whom It May Concern
17 | Print time cards
18 | Print signing on sheets for competitors
Print signing on sheets for Marshals
Print signing on sheets for Under 18s
19 | Print opening car instructions
Print closing car instructions
20 | Confirm arrangements with start venue , numbers attending and food requirements
Confirm costs of food
21 | Drive route to check for any issues e.g. road works
22 | Arrange for sign on marshals and their instructions/paperwork
23 | Collate competitor packs
Put navigational instructions into envelopes
Collate marshal packs
On the night
24/25 | Arrive and set up start venue
26 | At end of event, work out and announce provisional results
27 | Thank all marshals and competitors for attending
28 | Carry out marshals draw
29 | Pay for food
30 | Pass on code boards and clocks to next organiser
After the event
31 | Collate results onto speadsheet
Deal with any result protests
Post final results and circulate via Club Secretary (email), website and social media
32 | Scan in signing on sheets and send to Club Secretary for filing
33 | Complete club expenses form and send to Club Treasurer
Send any monies to Club Treasurer
34 | Send off documentation to insurance provider
Send invoice from insurance provider to Club Treasurer for payment
35 | Review event and invite feedback from competitors and marshals